## Schedule
Activity (Code) - Description | Number of Crews | Duration (Days)
(A) Engineering Survey and Layout | 8 | 6
(B) Temporary Access Road Construction | 8 | 12
(C) Construction Camp Setup | 10 | 9
(D) Site Clearing and Topsoil Stripping | 3 | 20
(E) Equipment Mobilization and Calibration | 9 | 14
(F) Subgrade Excavation (Soft Soil Treatment) | 3 | 9
(G) Earthwork Hauling and Spoil Area Management | 2 | 7
(H) Subgrade Compaction (Layered) | 3 | 13
(I) Dynamic Compaction for High Fill Zones | 3 | 18
(J) Preliminary Slope Grading | 3 | 18
(K) Graded Crushed Stone Base Paving | 10 | 18
(L) Cement-Stabilized Aggregate Base Construction | 4 | 8
(M) Subgrade Compaction Testing | 10 | 13
(N) Subgrade French Drain Excavation | 7 | 18
(O) Permeable Geotextile Installation | 9 | 6
(P) Stormwater Pipe Trench Excavation | 5 | 18
(Q) HDPE Double-Wall Corrugated Pipe Installation | 4 | 19
(R) Manhole Construction and Waterproofing | 3 | 8
(S) Pipe Backfilling (Sand-Gravel Layered Compaction) | 6 | 6
(T) Side Ditch and Interceptor Concrete Pouring | 4 | 12
(U) Lower Asphalt Layer Paving (AC-25) | 4 | 18
(V) Intermediate Asphalt Layer Paving (AC-20) | 2 | 12
(W) Surface Asphalt Layer Paving (SMA-13) | 7 | 11
(X) Thermoplastic Road Marking Application | 10 | 13
(Y) Anti-Skid Wear Layer Treatment | 9 | 7
(Z) Bridge Pile Drilling and Grouting | 2 | 7
(AA) Pier Formwork and Concrete Placement | 7 | 18
(AB) Precast T-Beam Installation | 5 | 14
(AC) Bridge Deck Pavement and Waterproofing | 3 | 9
(AD) Culvert Foundation Excavation and Bedding | 6 | 18
(AE) Reinforced Concrete Box Culvert Assembly | 5 | 5
(AF) W-Beam Guardrail Installation | 6 | 12
(AG) Traffic Sign Foundation Pre-Embedding | 9 | 16
(AH) Solar-Powered Warning Light Installation | 3 | 10
(AI) Speed Bump and Rumble Strip Installation | 5 | 11
(AJ) Surveillance Camera Pole and Wiring | 2 | 13
(AK) Slope Hydroseeding with Exogenous Soil | 5 | 19
(AL) Arbor Planting in Central Median Strip | 8 | 17
(AM) Noise Barrier Foundation Construction | 2 | 6
(AN) Ecological Swale Vegetation Restoration | 8 | 9
(AO) Construction Waste Removal and Site Reclamation | 4 | 11
(AP) Toll Station Steel Canopy Installation | 7 | 18
(AQ) Toll Island Concrete Placement | 3 | 11
(AR) Cable Trench Excavation and Conduit Pre-Embedding | 5 | 8
(AS) Tunnel Lighting System Commissioning | 2 | 14
(AT) Service Area Building Structural Work | 4 | 12
(AU) Full-Load Smoothness and Deflection Testing | 4 | 19
(AV) Completion Documentation Preparation | 6 | 19
(AW) Defect Liability Period Rectifications | 3 | 18
(AX) As-Built Drawing Finalization and Archiving | 5 | 16
(AY) Temporary Facility Dismantling and Demobilization | 8 | 16
(AZ) Project Completion Ceremony | 5 | 19